## Universe Migration
Metadata Extraction utility | [5 empty] | Without utility | [5 empty] | Metadata Extraction + Python script |  | 4 | 6 | 8 | 12
|  | Effort in PDS | [5 empty] | Effort in PDS | [5 empty] | Effort in PDS
Activities | Phase wise | Simple | Medium | Complex | Very Complex | Activities | Phase wise | Simple | Medium | Complex | Very Complex | Activities | Phase wise | Simple | Medium | Complex | Very Complex
Analyis of As is Universe | 10% | 0.51282 | 0.76923 | 1.0256 | 1.5385 | Analyis of As is Universe | 17% | 0.95775 | 1.4366 | 1.9155 | 2.8732 | Analyis of As is Universe | 10% | 0.51282 | 0.76923 | 1.0256 | 1.5385
Design equivalent models in Qlik | 10% | 0.51282 | 0.76923 | 1.0256 | 1.5385 | Design equivalent models in Qlik | 10% | 0.56338 | 0.84507 | 1.1268 | 1.6901 | Design equivalent models in Qlik | 10% | 0.51282 | 0.76923 | 1.0256 | 1.5385
Data Model Migration and Unit testing | 78% | 4 | 6 | 8 | 12 | Data Model Migration and Unit testing | 71% | 4 | 6 | 8 | 12 | Data Model Migration and Unit testing | 78% | 2 | 4.2 | 6 | 10.8
Deployment | 2% | 0.10256 | 0.15385 | 0.20513 | 0.30769 | Deployment | 2% | 0.11268 | 0.16901 | 0.22535 | 0.33803 | Deployment | 2% | 0.10256 | 0.15385 | 0.20513 | 0.30769
| Total | 5.1282 | 7.6923 | 10.2564 | 15.3846 |  | Total | 5.6338 | 8.4507 | 11.2676 | 16.9014 |  | Total | 3.1282 | 5.8923 | 8.2564 | 14.1846
[6 empty] | Saving by ME utility |  | 0.5056 | 0.7584 | 1.0112 | 1.5168 | Saving by ME + Python script |  | -2.5056 | -2.5584 | -3.0112 | -2.7168
Automation: (Metadata Extraction)
Convert Excel dump into SQL Scripts for QVF's implementaton

## Report Migration
|  | 0.75 | 1.5 | 2.5 | 4.5
Effort in PDS
Activities for Report Migration | Phase wise | Simple | Medium | Complex | Very Complex
Analysis of As is Reports | 10% | 0.15625 | 0.3125 | 0.48958 | 0.72917
Design for reports and Wireframe | 16% | 0.25 | 0.5 | 0.78333 | 1.1667
Report build on Qlik and Unit Testing | 48% | 0.75 | 1.5 | 2.35 | 3.5
Data Model Refinement | 9% | 0.14062 | 0.28125 | 0.44063 | 0.65625
System Testing and Report comparison | 15% | 0.23438 | 0.46875 | 0.73438 | 1.0938 | IVS
Deployment | 2% | 0.03125 | 0.0625 | 0.097917 | 0.14583
| Total | 1.5625 | 3.125 | 4.8958 | 7.2917

## Overall Efforts
Metadata Extraction utility |  |  |  |  | Without utility |  |  |  |  | Metadata Extraction + Python script | [8 empty] | Project Management
Universe Migration |  |  |  |  | Universe Migration |  |  |  |  | Universe Migration | [8 empty] | Efforts Summary
Total Universe |  | 698 |  |  | Total Universe |  | 698 |  |  | Total Universe |  | 698 | [7 empty] | Efforts (PDS) | PM
[19 empty] | Universe Migration | 4742.8205 | 225.8486
| Breakup | Universe | Efforts |  |  | Breakup | Universe | Efforts |  |  | Breakup | Universe | Efforts |  | 9103 | 7282.4 | rationalization |  | Report Migration | 11817.4688 | 562.7366
Simple | 60% | 418.8 | 2147.6923 |  | Simple | 60% | 418.8 | 2359.4366 |  | Simple | 60% | 418.8 | 1310.0923 |  |  | 5825.92 | personal reports |  | Report Rationalization | 1995 | 95
Medium | 25% | 174.5 | 1342.3077 |  | Medium | 25% | 174.5 | 1474.6479 |  | Medium | 25% | 174.5 | 1028.2077 |  |  | 4194.6624 |  |  | SIT Support | 620.4171 | 29.5437
Complex | 10% | 69.8 | 715.8974 |  | Complex | 10% | 69.8 | 786.4789 |  | Complex | 10% | 69.8 | 576.2974 | [5 empty] | UAT Support |  | 95
V Complex | 5% | 34.9 | 536.9231 |  | V Complex | 5% | 34.9 | 589.8592 |  | V Complex | 5% | 34.9 | 495.0431 | [5 empty] | SQL Scripts |  | 19
|  | PDS | 4742.8205 |  |  |  | PDS | 5210.4225 |  |  |  | PDS | 3409.6405 |  |  |  | 7100.34 |  | Self Service BI |  | 90.2
|  | PM | 225.8486 |  |  |  | PM | 248.1154 |  |  |  | PM | 162.3638 |  |  |  | 1988.0952 |  |  |  | 1117.3289
[5 empty] | Saving by ME utility |  |  |  |  | Saving by ME + Python utility | [8 empty] | Project Management | 8% | 89.3863
[6 empty] | PDS | 467.602 |  |  |  | PDS | 1800.782 |  |  |  | 9103 | 2002.66 |  |  |  | 1206.7152 | without pilot
[6 empty] | PM | 22.2668 | 9.8592 | % saving |  | PM | 85.7515 | 34.5612 | % saving |  | 4551.5 | 50%
Reports Migration | [15 empty] | 22% | Repot Rationalization |  | Self Service BI
Total Reports |  | 4194 |  |  | 4551.5 | [10 empty] | 28% | Self BI | [6 empty] | 134
[16 empty] | 2548.84 |  | SIT |  |  |  |  | 1820 | 108
| Breakup | Reports | Efforts | [6 empty] | Breakup | Reports | Efforts | [5 empty] | 491.4844 | Support of the reports for 1 yr |  |  |  |  | 26
Simple | 50% | 2097 | 3276.5625 | [5 empty] | Simple | 0.5 | 2275.75 | 3555.8594 | [5 empty] | 589.7812 | Analysis/Build/Test/Training | 1894.2 | 90.2
Medium | 30% | 1258.2 | 3931.875 | [5 empty] | Medium | 0.3 | 1365.45 | 4267.0312 | [5 empty] | 461.9953 |  |  | 90.2
Complex | 15% | 629.1 | 3079.9688 |  | PDS | 1694.7969 |  |  | Complex | 0.15 | 682.725 | 3555.8594 | [5 empty] | 229.3594 |  |  |  | 49.5
V Complex | 5% | 209.7 | 1529.0625 |  | PM | 80.7046 |  |  | V Complex | 0.05 | 227.575 | 2133.5156 | [5 empty] | 1772.6203
|  | PDS | 11817.4688 | [7 empty] | PDS | 13512.2656 | [5 empty] | 84.4105
|  | PM | 562.7366 |  |  | 12.5427 |  |  |  |  | PM | 643.4412
SSBI capability for 1 team/group
SQL migration | [18 empty] | Analysis | 1 | 1 | 1
Total Reports |  | 1365.45 | 1365.45 | [15 empty] | Build | 1.7 | 1 | 1
Testing
|  | Reports | Effort per script (hrs) | Efforts | [14 empty] | Training |  | 0.5 | 1 |  |  | 1 | 1 | 1
Simple | 60% | 819.27 | 2 | 1638.54 | [14 empty] | Total efforts (PM) | 8.2
Medium | 25% | 341.3625 | 2.5 | 853.4062
Complex | 15% | 204.8175 | 3.5 | 716.8612
|  | PHS |  | 3208.8075
|  | PDS |  | 401.1009
|  | PM |  | 19.1

## Effort Distribution
|  | Universe | Efforts in PM |  | Reports | Efforts in PM | Reports Per Universe | Total Efforts Reports + Universe | Effor per month | Duration |  | DNA | IVS
| UK | 234 | 75.7143 |  | 1993.893 | 267.5338 | 8.5209 | 343.248 | 57.208 | 6 | 12 | 285.1429 | 3.4286
| HK | 271 | 87.6862 |  | 1726.01 | 231.5901 | 6.369 | 319.2763 | 63.8553 | 5 | 10 | 237.619 | 2.8571
| US | 68 | 22.0024 |  | 2054.03 | 275.6027 | 30.2063 | 297.6052 | 49.6009 | 6 | 12 | 285.1429 | 3.4286
| FR | 125 | 40.4457 |  | 1335.51 | 179.1942 | 10.6841 | 219.6398 | 54.91 | 4 | 8 | 190.0952 | 2.2857
|  | 698 |  |  | 4194
Universe Migration Effort |  | 225.8486 |  | Reports | 562.7366

## Schedule
|  | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01
Pilot | Pilot Kick off and Planning
Approach for migration
Utility Development
Pilot for 1 universe and 10 reports
Report Rationalization
US | Universe Migration
Report Migration and Build
System Testing and Report Comparison
User Testing
UAT Support
Deployment
FR | Universe Migration
Report Migration and Build
System Testing and Report Comparison
User Testing
UAT Support
Deployment
UK | Universe Migration
Report Migration and Build
System Testing and Report Comparison
User Testing
UAT Support
Deployment
HK | Universe Migration
Report Migration and Build
System Testing and Report Comparison
User Testing
UAT Support
Deployment
PM | Project Management

## Staffing
Phase | Desc | Role | SL | Location | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | Effort | Rate | Cost
Pilot Phase |  | Architect | DNA | UK | 1 | 1 | [14 empty] | 2 | 93.75 | 30000
|  | Technical Lead | DNA | UK | 1 | 1 | [14 empty] | 2 | 75 | 24000
| Subcons | Consultant | DNA | UK | [16 empty] | 0 | 162.5 | 0
|  | Technical Lead | DNA | India | 1 | 1 | [14 empty] | 2 | 27.25 | 8720
|  | Technical Analyst | DNA | India | 2 | 2 | [14 empty] | 4 | 23 | 14720
|  | Technical Test lead | IVS | India | [16 empty] | 0 | 24.75 | 0
|  | Developer | DNA | India | 4 | 4 | [14 empty] | 8 | 20 | 25600
|  | Project Manager | DNA | India | 1 | 1 | [14 empty] | 2 | 29.75 | 9520
Report Rationalization |  | Principal Consultant | DNA | UK | 0 | 0 |  |  |  | 1 | 1 | 1 | 0 | [7 empty] | 3 | 125 | 60000
|  | Principal Consultant | DNA | India | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 9 | 45.38 | 65347.2
|  | Snr Consultant | DNA | India | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 12 | 34.13 | 65529.6
|  | Consultant | DNA | UK |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | [5 empty] | 3 | 89.875 | 43140
|  | Consultant | DNA | India |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 |  |  | 9 | 33.75 | 48600
|  | Sr Associate consultant | DNA | India | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 |  |  |  | 23 | 27.25 | 100280
|  | Associate consultant | DNA | India | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 2.5 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 29.5 | 25.625 | 120950
US | Universe Migration & Reports Dev | Architect | DNA | UK |  |  | 1 | 1 | 1 | 1 | 1 | 1 | [8 empty] | 6 | 93.75 | 90000
|  | Technical Lead | DNA | UK |  |  |  |  | 1 | 1 | 1 | 1 | [8 empty] | 4 | 75 | 48000
|  | Technical Analyst | DNA | UK | [16 empty] | 0 | 70.15 | 0
|  | Architect | DNA | India |  |  | 1 | 1 | 1 | 1 | 1 | 1 | [8 empty] | 6 | 35 | 33600 |  | 184
|  | Technical Lead | DNA | India |  |  | 3 | 3 | 3 | 3 | 3 | 3 | [8 empty] | 18 | 27.25 | 78480 |  | 11
|  | Technical Analyst | DNA | India |  |  | 6 | 7 | 9 | 7 | 7 | 7 | [8 empty] | 43 | 23 | 158240 |  | 24
|  | Developer | DNA | India |  |  | 18 | 17 | 17 | 17 | 19 | 19 | [8 empty] | 107 | 20 | 342400
| SIT | Technical Test Lead | IVS | UK |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | 6 | 70.15 | 67344
|  | Technical Test Lead | IVS | India |  |  |  |  | 1 | 1 | 1 | 1 | 1 | [7 empty] | 5 | 24.75 | 19800
|  | Test Analyst | IVS | India |  |  |  |  | 1 | 1 | 1 | 1 | 1 | [7 empty] | 5 | 21 | 16800
|  | Test Engineer | IVS | India |  |  |  |  | 2 | 3 | 3 | 3 | 3 | [7 empty] | 14 | 18 | 40320
| SIT Support | Technical Lead | DNA | UK | [16 empty] | 0 | 75 | 0
|  | Technical Analyst | DNA | UK | [16 empty] | 0 | 70.15 | 0
|  | Technical Lead | DNA | India | [5 empty] | 1 | 1 | 1 | [8 empty] | 3 | 27.25 | 13080
|  | Technical Analyst | DNA | India | [5 empty] | 2 | 3 | 2 | 1 | [7 empty] | 8 | 23 | 29440
| UAT | Technical Lead | DNA | UK | [8 empty] | 1 | 1 | [6 empty] | 2 | 75 | 24000
|  | Technical Lead | DNA | India | [7 empty] | 3 | 2 | 2 | [6 empty] | 7 | 27.25 | 30520
|  | Technical Analyst | DNA | India | [7 empty] | 2 | 2 | 2 | [6 empty] | 6 | 23 | 22080
|  | Test Analyst | IVS | India | [7 empty] | 3 | 3 | [7 empty] | 6 | 21 | 20160
FR | Universe Migration & Reports Dev | Architect | DNA | UK | [8 empty] | 1 | [7 empty] | 1 | 93.75 | 15000
|  | Technical Lead | DNA | UK | [6 empty] | 1 | 1 | 1 | 1 | [6 empty] | 4 | 75 | 48000
|  | Technical Analyst | DNA | UK | [16 empty] | 0 | 70.15 | 0
|  | Architect | DNA | India | [5 empty] | 1 | 1 | 1 | 1 | 1 | [6 empty] | 5 | 35 | 28000
|  | Technical Lead | DNA | India | [5 empty] | 6 | 6 | 6 | 3 | 2 | [6 empty] | 23 | 27.25 | 100280
|  | Technical Analyst | DNA | India | [5 empty] | 7 | 8 | 8 | 5 | 3 | [6 empty] | 31 | 23 | 114080
|  | Developer | DNA | India | [5 empty] | 12 | 17 | 18 | 18 | 18 | [6 empty] | 83 | 20 | 265600
| SIT | Technical Test Lead | IVS | UK | [9 empty] | 1 | [6 empty] | 1 | 70.15 | 11224
|  | Technical Test Lead | IVS | India | [8 empty] | 1 | 1 | 1 | [5 empty] | 3 | 24.75 | 11880
|  | Test Analyst | IVS | India | [8 empty] | 1 | 1 | 1 | [5 empty] | 3 | 21 | 10080
|  | Test Engineer | IVS | India | [8 empty] | 3 | 3 | 3 | [5 empty] | 9 | 18 | 25920
| SIT Support | Technical Lead | DNA | UK | [16 empty] | 0 | 75 | 0
|  | Technical Analyst | DNA | UK | [16 empty] | 0 | 70.15 | 0
|  | Technical Lead | DNA | India | [8 empty] | 1 | 1 | 1 | [5 empty] | 3 | 27.25 | 13080
|  | Technical Analyst | DNA | India | [8 empty] | 1 | 2 | 2 | [5 empty] | 5 | 23 | 18400
| UAT | Technical Lead | DNA | UK | [10 empty] | 1 | [5 empty] | 1 | 75 | 12000
|  | Technical Lead | DNA | India | [10 empty] | 3 | 2 |  |  |  |  | 5 | 27.25 | 21800
|  | Technical Analyst | DNA | India | [10 empty] | 3 | 3 |  |  |  |  | 6 | 23 | 22080
|  | Test Analyst | IVS | India | [9 empty] | 4 | [6 empty] | 4 | 21 | 13440
UK | Universe Migration & Reports Dev | Architect | DNA | UK | [8 empty] | 1 | 1 | 1 | 1 |  |  |  |  | 4 | 93.75 | 60000
|  | Technical Lead | DNA | UK | [8 empty] | 1 | 1 | 1 | 1 |  |  |  |  | 4 | 75 | 48000
|  | Technical Analyst | DNA | UK | [16 empty] | 0 | 70.15 | 0
|  | Architect | DNA | India | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 6 | 35 | 33600
|  | Technical Lead | DNA | India | [6 empty] | 7 | 7 | 6 | 6 | 6 | 6 |  |  |  |  | 38 | 27.25 | 165680
|  | Technical Analyst | DNA | India | [6 empty] | 8 | 9 | 10 | 10 | 10 | 8 |  |  |  |  | 55 | 23 | 202400
|  | Developer | DNA | India | [6 empty] | 22 | 22 | 22 | 21 | 19 | 13 |  |  |  |  | 119 | 20 | 380800
| SIT | Technical Test Lead | IVS | UK | [9 empty] | 1 | 1 | 1 | 1 |  |  |  | 4 | 70.15 | 44896
|  | Technical Test Lead | IVS | India | [9 empty] | 1 | 1 | 1 | 1 |  |  |  | 4 | 24.75 | 15840
|  | Test Analyst | IVS | India | [9 empty] | 1 | 1 | 1 | 1 |  |  |  | 4 | 21 | 13440
|  | Test Engineer | IVS | India | [9 empty] | 3 | 3 | 3 | 3 |  |  |  | 12 | 18 | 34560
| SIT Support | Technical Lead | DNA | UK | [16 empty] | 0 | 75 | 0
|  | Technical Analyst | DNA | UK | [16 empty] | 0 | 70.15 | 0
|  | Technical Lead | DNA | India | [9 empty] | 2 | 2 | 2 | 2 |  |  |  | 8 | 27.25 | 34880
|  | Technical Analyst | DNA | India | [9 empty] | 1 | 1 | 1 | 1 |  |  |  | 4 | 23 | 14720
| UAT | Technical Lead | DNA | UK | [11 empty] | 1 | 1 | 1 |  |  | 3 | 75 | 36000
|  | Technical Lead | DNA | India | [11 empty] | 1 | 1 | 1 |  |  | 3 | 27.25 | 13080
|  | Technical Analyst | DNA | India | [11 empty] | 5 | 5 | 4 |  |  | 14 | 23 | 51520
|  | Test Analyst | IVS | India | [10 empty] | 3 | 4 | 4 | 4 |  |  | 15 | 21 | 50400
HK | Universe Migration & Reports Dev | Architect | DNA | UK | [12 empty] | 1 | 1 |  |  | 2 | 93.75 | 30000
|  | Technical Lead | DNA | UK | [10 empty] | 1 | 1 | 1 | 1 |  |  | 4 | 75 | 48000
|  | Technical Analyst | DNA | UK | [16 empty] | 0 | 70.15 | 0
|  | Architect | DNA | India | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 6 | 35 | 33600
|  | Technical Lead | DNA | India | [8 empty] | 3 | 4 | 6 | 6 | 4 | 4 |  |  | 27 | 27.25 | 117720
|  | Technical Analyst | DNA | India | [8 empty] | 5 | 6 | 11 | 10 | 10 | 10 |  |  | 52 | 23 | 191360
|  | Developer | DNA | India | [8 empty] | 6 | 13 | 30 | 29 | 28 | 27 |  |  | 133 | 20 | 425600
| SIT | Technical Test Lead | IVS | UK | [12 empty] | 0 | 1 | 0 |  | 1 | 70.15 | 11224
|  | Technical Test Lead | IVS | India | [12 empty] | 1 | 1 | 1 |  | 3 | 24.75 | 11880
|  | Test Analyst | IVS | India | [12 empty] | 1 | 1 | 1 |  | 3 | 21 | 10080
|  | Test Engineer | IVS | India | [12 empty] | 3 | 3 | 3 |  | 9 | 18 | 25920
| SIT Support | Technical Lead | DNA | UK | [16 empty] | 0 | 75 | 0
|  | Technical Analyst | DNA | UK | [16 empty] | 0 | 70.15 | 0
|  | Technical Lead | DNA | India | [12 empty] | 1 | 1 | 1 |  | 3 | 27.25 | 13080
|  | Technical Analyst | DNA | India | [12 empty] | 2 | 2 | 2 |  | 6 | 23 | 22080
| UAT | Technical Lead | DNA | UK | [14 empty] | 1 | 1 | 2 | 75 | 24000
|  | Technical Lead | DNA | India | [13 empty] | 2 | 1 | 1 | 4 | 27.25 | 17440
|  | Technical Analyst | DNA | India | [13 empty] | 2 | 2 | 1 | 5 | 23 | 18400
|  | Test Analyst | IVS | India | [13 empty] | 3 | 3 | 3 | 9 | 21 | 30240
SQL Migration |  | Technical Lead | DNA | UK | [16 empty] | 0 | 75 | 0
|  | Technical Analyst | DNA | India |  |  | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | 18 | 23 | 66240
Project Management |  | Program Manager (Industry Principal) | DNA | UK |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 13 | 145 | 301600
|  | Project Manager | DNA | UK | [16 empty] | 0 | 90 | 0
|  | Project Manager (Testing) | IVS | India |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 13 | 25.625 | 53300
|  | Program Manager | DNA | India |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 14 | 34.875 | 78120
|  | Project Manager | DNA | India |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 32 | 29.75 | 152320
Automation |  | Technical Lead | DNA | UK | [16 empty] | 0 | 75 | 0
|  | Technical Lead | DNA | India |  |  | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 28 | 27.25 | 122080
Self Service BI |  | Principal Consultant | DNA | UK | 0 | 0 | 0 | 0 | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  | 5 | 125 | 100000 |  |  | 83
|  | Principal Consultant | DNA | India | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 11 | 45.38 | 79868.8
|  | Sr Associate consultant | DNA | UK |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 75 | 0
|  | Sr Associate consultant | DNA | India |  |  | 2 | 2 | 2 | 2 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 17.5 | 27.25 | 76300
|  | Architect | DNA | India |  |  |  | 1 | 1 | 1 | 1 | 1 | [8 empty] | 5 | 35 | 28000
|  | Technical Lead | DNA | India |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 8 | 27.25 | 34880
|  | Technical Analyst | DNA | India |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 8 | 23 | 29440
|  | Developer | DNA | India |  |  |  |  | 3 | 3 | 4 | 4 | 3 | 3 | 0.5 | [5 empty] | 20.5 | 20 | 65600
|  | Test Analyst | IVS | India | [16 empty] | 0 | 21 | 0
|  | Test Engineer | IVS | India | [16 empty] | 0 | 18 | 0
| Trainer | Snr Consultant | DNA | India | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 16 | 34.13 | 87372.8
[21 empty] | 1316.5 |  | 5887096.4 |  |  | 1284.5
646.7205
[5 empty] | 16 | 16 | 51 | 55 | 65 | 93 | 141.5 | 149.5 | 131 | 140 | 135.5 | 119 | 87 | 83 | 23 | 11 | 1316.5
3858.7163
327990.8849

## Parameters
| Universe | Sources | Tables | Filters | Calculated Fields | Stored Procedure | Schema | Security
1 | Simple Universe | 1 | <10 dimension tables and 2 Fact table | <=15 | <=15 | 0 | Star Schema | Simple data security logic
2 | Medium Universe | 1 | <20 dimension tables and 4 Fact table | <=25 | <=25 | 1 | Star/Snow flake schema | Standard data security (based on 2 to 3 fields/columns)
3 | Complex Universe | <=2 | <=25 dimension tables and 4 to 5 Fact tables | <=40 | <=40 | 2 | Star/Snow flake schema | Complex data security (based on 3 to 4 fields/columns)
4 | V Complex Universe | >2 | >25 dimension tables and >=5 Fact tables | >=50 | >=50 | >2 | Star/Snow flake schema | Complex data security (> 4 fields/columns)
| Report | Sources | Attributes | Filters | Calculated Fields | Master Items | Data Providers
1 | Simple Report | 1 | <3 Chart/table with simple expressions. | <=3 | <=3 | <=5 | <=5
2 | Medium Report | 1 | <6 Chart/table with Medium complex expressions. | <5 | <5 | <8 | <=15
3 | Complex Report | <=2 | <10 Chart/table with Complex set analysis | <8 | <8 | <10 | <=25
4 | V Complex Report | >2 | >10 Chart/table with Complex set analysis,(If conditions, Calculated fields in expresssion, Variables) | >=8 | >8 | >=10 | >25

## Assumptions
Sr.No. | Assumptions
1 | Assumed 7108 BO reports needs to be converted as around 20% of total reports possibly can be consolidated. Complexity Split taken as SMC - Simple-50%, Medium-30%, Complex-15% and V Complex-5%
2 | Assumed 698 BO universes needs to be converted. Complexity Split taken as SMC - Simple-60%, Medium-25%, Complex-10% and V Complex-5%
3 | 20% to 30% reports are using either Free hand SQL or Stored proceedures
4 | Report Specification - Qlik Sense reports should be similar to BO reports, so many design changes will not required
5 | Wireframes - 4-5 categories will be created and get it approved from businesss. Same kind of reports will be created. No need to create wireframe for each and every report
6 | The complexity definition is a guideline used to determine a report, data model and schedule complexity. If few of the conditions specified in the definition are met, the complexity is changed to appropriate complexity (i.e. starting from Simple to Medium or Complex)
7 | In some cases, need to take a logical decision to create multiple data models if single data model is becoming very complex as report performance can become slow with complex data models
8 | The focus will be on As Is migration and consolidation wherever possible, and not on leveraging capabilities and features of target platform at the time of migration
9 | Most of the SAP BO reports are simple tabular reports, effort/unit modified accordingly
10 | SIT: System Testing and Report comparison is 15% as per standard guidelines

## ResourcePlan
SL | DNA
Row Labels | Sum of Cost | Sum of Jun-20 | Sum of Jul-20 | Sum of Aug-20 | Sum of Sep-20 | Sum of Oct-20 | Sum of Nov-20 | Sum of Dec-20 | Sum of Jan-21 | Sum of Feb-21 | Sum of Mar-21 | Sum of Apr-21 | Sum of May-21 | Sum of Jun-21 | Sum of Jul-21 | Sum of Aug-21 | Sum of Sep-21
UK | 1877048 | 4 | 4 | 7 | 7 | 8 | 13 | 14 | 15 | 10 | 11 | 10 | 8 | 6 | 5 | 3 | 1
Grand Total | 1877048 | 4 | 4 | 7 | 7 | 8 | 13 | 14 | 15 | 10 | 11 | 10 | 8 | 6 | 5 | 3 | 1

## Staffing-OnsiteOffshoreRatio
Row Labels | Sum of Effort | Sum of Cost | Ratio
India | 1235.5 | 4693228.4 | 94.13%
UK | 77 | 1176428 | 5.867%
Grand Total | 1312.5 | 5869656.4